## Sheet1
|  | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE
TASK TITLE | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
|  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Setup
Design Gantt Chart | 100% | bar: WEEK 1 T to WEEK 1 W; WEEK 2 M; WEEK 2 W; WEEK 5 M; WEEK 5 W; WEEK 8 M; WEEK 8 W
Design game rules | 100% | bar: WEEK 1 W to WEEK 1 R; WEEK 2 M; WEEK 2 W; WEEK 5 M; WEEK 5 W; WEEK 8 M; WEEK 8 W
Create game flow design | 75% | bar: WEEK 1 W to WEEK 1 R; WEEK 2 M; WEEK 2 W; WEEK 5 M; WEEK 5 W; WEEK 8 M; WEEK 8 W
Create UML chart | 75% | bar: WEEK 1 W to WEEK 1 R; WEEK 2 M; WEEK 2 W; WEEK 5 M; WEEK 5 W; WEEK 8 M; WEEK 8 W
Create github repo | 100% | bar: WEEK 1 W to WEEK 1 R; WEEK 2 M; WEEK 2 W; WEEK 5 M; WEEK 5 W; WEEK 8 M; WEEK 8 W
Design
Software design | 0% | bar: WEEK 2 M; WEEK 2 W; WEEK 3 M; WEEK 3 W; WEEK 5 M; WEEK 5 W; WEEK 8 M; WEEK 8 W
Interface design | 0% | bar: WEEK 2 M; WEEK 2 W; WEEK 5 M; WEEK 5 W; WEEK 8 M; WEEK 8 W
Implement card designs | 0% | bar: WEEK 2 M; WEEK 2 W; WEEK 5 M; WEEK 5 W; WEEK 8 M; WEEK 8 W
Create design specifications | 0% | bar: WEEK 2 M; WEEK 2 W; WEEK 3 M; WEEK 3 W; WEEK 5 M; WEEK 5 W; WEEK 8 M; WEEK 8 W
Design Finished | 0% | bar: WEEK 2 M; WEEK 2 W; WEEK 3 W; WEEK 5 M; WEEK 5 W; WEEK 8 M; WEEK 8 W
Development
Create sub-classes | 0% | bar: WEEK 2 M; WEEK 2 W; WEEK 4 M; WEEK 4 W; WEEK 5 M; WEEK 5 W; WEEK 8 M; WEEK 8 W
Integrate classes into a main module / program | 0% | bar: WEEK 2 M; WEEK 2 W; WEEK 5 M; WEEK 5 W; WEEK 8 M; WEEK 8 W
Perform initial testing | 0% | bar: WEEK 2 M; WEEK 2 W; WEEK 4 M; WEEK 4 W; WEEK 5 M; WEEK 5 W; WEEK 8 M; WEEK 8 W
Documentation | 0% | bar: WEEK 2 M; WEEK 2 W; WEEK 5 M; WEEK 5 W; WEEK 6 M; WEEK 6 W; WEEK 8 M; WEEK 8 W
Testing
Setup unit-testing for each sub-class | 0% | bar: WEEK 2 M; WEEK 2 W; WEEK 4 M; WEEK 4 W; WEEK 5 M; WEEK 5 W
Document issues found | 0% | bar: WEEK 2 M; WEEK 2 W; WEEK 4 M; WEEK 4 W; WEEK 5 M; WEEK 5 W; WEEK 7 M; WEEK 7 W; WEEK 8 M; WEEK 8 W; WEEK 9 M; WEEK 9 W
Correct issues found | 0% | bar: WEEK 2 M; WEEK 2 W; WEEK 5 M; WEEK 5 W; WEEK 7 M; WEEK 7 W; WEEK 8 M; WEEK 8 W; WEEK 9 M; WEEK 9 W
Final cleanup of code | 0% | bar: WEEK 2 M; WEEK 2 W; WEEK 5 M; WEEK 5 W; WEEK 8 M; WEEK 8 W; WEEK 9 M; WEEK 9 W